## 1
Please ensure this tracking sheet is completed as a group, as it will be used to monitor your individual participation within the team.
Team Members | Role/ Responsibilty | Email
Ntakirutimana Pretty | Group member | p.ntakiruti@alustudent.com
Harerimana Egide | Group member | h.egide@alustudent.com
Task Allocation and Tracker
| Task Allocated | Assigned Member | Deadline | Completion Status (Not Started/In Progress/Completed/Did not participate) | Reviewed by Team? (Yes/No) | Comments
| Data collection | Pretty | 2026-03-03 | Completed | Yes | She collected data standing, still, jumbing and walking
| Data collection | Egide | 2026-03-03 | Completed | Yes | He collected data standing, still, jumbing and walking
| Feature Extraction & Normalization Scripting | Egide | 2026-03-04 | Completed | Yes | He extracted features from the data.
| HMM Implementation (Baum-Welch & Viterbi) | Pretty & Egide | 2026-03-04 | Completed | Yes | We implemented the model.
| Visualizations (Transition/Confusion Matrices) | Egide | 2026-03-04 | Completed | Yes | We visualised the results using confusion matrices for data driven decision making
| Report Writing and Formatting | Pretty & Egide | 2026-03-08 | Completed | Yes | We wrote a report detailing the data, model and results
Meeting Attendance Log
Meeting Date | Agenda | Facilitator | Attendees | Key Discussion Points | Next Steps
2026-03-01 | Discussing the assignment and data collection | Pretty | Pretty & Egide | How to do the assignment Data collection | Data collection, feature extraction, model creation.
2026-03-03 | Reviewing the collected data, feature extration and model creation | Egide | Pretty & Egide | Reviewing collected data Feature extraction Creation of the model | Report creation.
2026-03-08 | Discussing the report and assignment submission. | Egide | Pretty & Egide | Report creation | Assignment submission.